## Sheet1
Team Bracketed | Luke Myers, William Braun, Sam Winkelmann, Michael Rhode
Timeline
Person | Task | Start Date | End Date
| Conduct interviews and gather insights from potential users to understand expectations, preferred features, and usability needs | 2025-10-05 | 2025-10-19
Sam | Interview people to gain insight into what a user would want out of the game/UI. | 2025-10-05 | 2025-10-19
| Create and refine wireframes and interface mockups. Review the design as a team to finalize the visual layout | 2025-10-19 | 2025-11-09
Sam | Sketch mockups of the interface of the website. | 2025-10-05 | 2025-11-09
Luke | Research potential third party services such as user authentication and automated email messaging, and decide if it would be better to implement our own or use the third-party providers. | 2025-10-19 | 2025-11-02
Michael | Research statistics that would be important to calculate to show player/team skill. | 2025-10-19 | 2025-11-09
| Select the frontend, backend, and database frameworks. Install all necessary software for selected frameworks on developer environments | 2025-10-05 | 2025-10-19
Michael | Discover and decide on a database option for holding data to be used in internal data calculations. | 2025-10-05 | 2025-10-19
Luke | Analyze benefits and drawbacks of different front and backend frameworks to determine what will work best for our application. | 2025-10-05 | 2025-10-12
| Set up the backend server structure and connect it to a test database and the frontend | 2025-10-19 | 2025-11-23
Michael | Learn how to connect a database to an API that has live updated information from the games being played. | 2025-10-05 | 2025-10-26
Michael | Develop data tables in a database to hold data imported from an API. | 2025-10-26 | 2025-11-23
William | Design and implement API endpoints that allow the frontend to retrieve and update user predictions, leaderboards, and match results. | 2025-10-19 | 2025-11-23
Luke | Determine what information about sports leagues (Teams, Games, Schedules etc) should be stored locally vs gotten from APIs to maximize space and time optimization. | 2025-10-19 | 2025-11-02
Sam | Implement decided upon design for the front-end of the website. | 2025-10-19 | 2025-11-23
| Create multiple database tables for different sections of our data: team data, user data, current and past leagues, etc. so that other functions can be implemented and tested properly. | 2025-10-19 | 2025-11-23
William | Integrate external sports and Esports APIs into the backend system to collect game data and make it accessible to the application. | 2025-10-10 | 2025-11-23
| Finish a simplified version of the final application. Users will be able to create a challenge and select the winners for each game. Third party API’s for live score updates will be used and results and records will be displayed. | 2025-11-23 | 2025-01-11
Luke | Create a straightforward development environment where the front and backend can either run locally or online, and real vs test data can be used. | 2025-11-23 | 2025-12-07
Sam | Develop initial barebones website so we can connect backend/database. | 2025-11-23 | 2025-01-04
William | Develop logic for scoring and leaderboard updates to ensure user predictions are processed correctly and results are reflected accurately. | 2025-11-23 | 2025-01-11
| Finalize user account creation, authentication, and leaderboard ranking features. Verify scoring logic accuracy and display rankings dynamically | 2025-01-11 | 2026-02-08
William | Implement backend authentication to handle user login and registration. | 2025-01-11 | 2025-02-01
William | Test backend to frontend communication by verifying that data transfers smoothly between the UI and database. | 2025-02-01 | 2025-02-08
| Conduct end-to-end testing across the frontend, backend, and database. Validate data accuracy, API performance, and usability feedback | 2026-02-08 | 2026-02-22
| Review all components for consistency, prepare documentation, and create presentation materials for the final project demonstration | 2026-02-22 | 2026-03-15
Michael | Document all progress with respect to the database and its connection to the API and issues that arise and need to be solved. | 2025-10-05 | 2026-03-15